## HMS_WBS_Shadril
Week | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 1 | 2023-11-01 | 2023-11-01
|  |  | 1.1.2 Develop project schedule | 2 | 2023-11-01 | 2023-11-01
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-11-01 | 2023-11-03
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 1 | 2023-11-01 | 2023-11-04
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-11-02 | 2023-11-05
|  |  | 1.2.3 Understanding Functional Requirements | 1 | 2023-11-02 | 2023-11-02
|  |  | 1.2.4 Identifying Non-Functional Requirements | 2 | 2023-11-02 | 2023-11-02
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-11-02 | 2023-11-02
|  |  | 1.3.2 Prepare UML DFD diagram | 1 | 2023-11-02 | 2023-11-02
|  |  | 1.3.3 Prepare UML ERD diagram | 3 | 2023-11-02 | 2023-11-02
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-11-03 | 2023-11-03
|  |  | 1.3.5 Prepare UML Class diagram | 2 | 2023-11-03 | 2023-11-03
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze Authentication Authorization API | 2 | 2023-11-03 | 2023-11-03
|  |  | 2.1.2 Analyze User Creation API | 2 | 2023-11-03 | 2023-11-03
|  |  | 2.1.3 Analyze Appointment Scheduling API | 2 | 2023-11-03 | 2023-11-03
|  |  | 2.1.4 Analyze Pharmaceutical API | 2 | 2023-11-03 | 2023-11-03
|  |  | 2.1.5 Analyze Community and Help Desk API | 2 | 2023-11-03 | 2023-11-03
|  |  | 2.1.6 Analyze implementation of Notification and Alert | 2 | 2023-11-03 | 2023-11-03
|  |  | 2.1.7 Analyze CDSS and Optional Features | 2 | 2023-11-06 | 2023-11-06
|  |  | 2.1.8 Prepare documentation about API responses | 4 | 2023-11-06 | 2023-11-06
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 3 | 2023-11-06 | 2023-11-06
|  |  | 2.2.2 Design doctor, patient and admin dashboard | 4 | 2023-11-06 | 2023-11-06
|  |  | 2.2.3 Design pharmaceutical page | 1 | 2023-11-07 | 2023-11-07
|  |  | 2.2.4 Design help desk for patient | 1 | 2023-11-07 | 2023-11-07
|  |  | 2.2.5 Design appointment schedule page | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.2.6 Design user profile | 1 | 2023-11-07 | 2023-11-07
|  | 2.3 Design database | 2.3.1 Identifying database entities | 3 | 2023-11-07 | 2023-11-07
|  |  | 2.3.2 Analyze relationship between entities | 1 | 2023-11-07 | 2023-11-07
3 | Development
|  | 3.3 Implement Log/Registration Feature | 3.3.1 Write register request and login request models | 2 | 2023-11-08 | 2023-11-08
|  |  | 3.3.2 Complete registration functionality | 6 | 2023-11-09 | 2023-11-09
|  |  | 3.3.3 Complete login functionality | 2 | 2023-11-10 | 2023-11-10
|  | 3.4 Implement Doctor Creation and Patient Creation Feature | 3.4.1 Create model classes | 1.5 | 2023-11-13 | 2023-11-13
|  | c | 3.4.2 Complete Patient and Doctor registration/login Feature | 3 | 2023-11-14 | 2023-11-14
|  | 3.5 Appointment Scheduling And Resource Allocation Feature | 3.5.1 Appointment Scheduling Feature | 3 | 2023-11-15 | 2023-11-15
|  |  | 3.5.2 Appointment booking Feature | 3 | 2023-11-16 | 2023-11-16
|  |  | 3.5.3 Resource Allocation Feature | 7 | 2023-11-17 | 2023-11-17
|  | 3.6 Implement Community and help desk for Patient | 3.6.1 Rearch about community feature | 2 | 2023-11-20 | 2023-11-20
|  |  | 3,6,2 Implement help desk for patients | 2 | 2023-11-21 | 2023-11-21
|  |  | 3.6.3 Implement community and review feature | 5 | 2023-11-22 | 2023-11-22
|  | 3.7 Implement CDSS and Optional features | 3.7.1 Implement Clinical Decision Support System | 2 | 2023-11-23 | 2023-11-23
|  |  | 3.7.2 Implement Optional Features | 2 | 2023-11-23 | 2023-11-23
c |  | 3.7 Front end development of authentication, authorization, appointment feature | 3.7.1 Complete login registration pages | 2 | 2023-11-24 | 2023-11-23
|  |  | 3.7.2 Implement appointment schedule and booking pages | 7 | 2023-11-27 | 2023-11-27
| c | 3.8 Front End of community, notification feature | 3.8.1 Complete community pages and implement notification | 8 | 2023-11-28 | 2023-11-28
4 | Quality Assurance and Project closing
| c | 4.1 Software testing and quality assurance | 4.1.1 Develop test cases | 3 | 2023-11-29 | 2023-11-29
|  |  | 4.1.2 Conduct Unit Testing / Integration Testing | 6 | 2023-11-29 | 2023-11-29
|  |  | 4.1.3 Fix bugs and defects | 8 | 2023-11-30 | 2023-11-30
|  | 4.2 Project Closing | 4.2.1 Revise the project deployment checklist | 4 | 2023-11-30 | 2023-11-30
|  |  | 4.2.2 Deploy the HMS application | 2 | 2023-11-30 | 2023-11-30